## PMP
Review No. | Raised By | Issue Date | Issue | Status | Assigend to | Closed date | Closed By | Document Status
Version 1.0 | [7 empty] | Draft
PMP_01 | Aya Ahmed | 14/4 | No issue found | Close
PMP_02 | Ashry | 15/4 | No issue found | Close
PMP_03 | Medhat | 15/4 | No issue found | Close
Version 1.1 |  |  | Version 1.0 |  |  |  |  | Draft
PMP_04 | Ashry | 25/4 | More required edits in escaltion | Close | Saad | 25/4 | Ashry
Version 1.2 | [7 empty] | Draft
PMP_05 | Medhat | 29/4 | Naming Convention is required | Close | Saad | 29/4 | Medhat
Version 1.3 | [7 empty] | Draft
PMP_06 | Amr | 8/5 | Revision History is missed | Close | Nada | 8/5 | Nada
Version 1.4 | [7 empty] | Draft
PMP_06 | Osama | 8/5 | Updating project schedule | Close | Nada | 5/10/2022 | Osama
PMP_06 | Amr | 8/5 | Revision History is missed | Close | Ashry | 5/10/2022 | Ashry
Version 1.5 | [7 empty] | Draft

## Project Charter
Review No. | Raised By | Issue Date | Issue | Status | Assigend to | Closed date | Closed By
PC_01 | Amr | 8/5 | In organizational goals , delivery date is missed. | Closed | Nada | 8/5 | Nada

## Sequence Diagrams
Review No. | Raised By | Issue Date | Issue | Status | Assigend to | Closed date | Closed By
SEQ_01 | Saad | 22/4 | Admin Add trip has some duplicated data | Close | Aya | 22/4 | Saad
SEQ_02 | Saad | 22/4 | No issues found | Close
SEQ_03 | Ashry | 22/4 | No issues found | Close
SEQ_04 | Amr | 6/5 | Home , Thank you page in Sequence_User_Book is redudant. | Close | Nada | 8/5 | Nada
SEQ_05 | Osama | 8/5 | low-level designs weren't accurate enough. | Close | Nada | 12/5 | Osama
SEQ_06 | Amr | 11/5 | the if-else should be in two blocks , db wasn't should be in the digram. | Close | Nada | 13/5 | Nada

## ERD diagram
Review No. | Raised By | Issue Date | Issue | Assigend to | Closed date | Closed By
ERD_01 | Nada | 21/4 | The relation "Book" between customer and destination is not recorded | Saad | 22/4 | Nada
ERD_02 | Nada | 22/4 | No issue found
ERD_03 | Medhat | 22/4 | No issue found
ERD_04 | Ashry | 29/4 | No issue found
ERD_06 | Ashry | 8/5 | In admin entity, name of the admin should be username, In User entity, username is missed. In Tour entity, start date should be end date. The relation between tour, and the user should be 1 to many. | Nada | 10/5 | Ashry
ERD_07 | Nada | 17/5 | No issue found

## Imapct Analysis
Review No. | Raised By | Issue Date | Issue | Assigend to | Closed date | Closed By
IA_01 | Nada | 21/4
IA_02 | Ahsry | 17/5 | 1-The impact summary needs to be clarified. 2-Add more than one solution like postponed to the next release | Nada
IA_03 | Osama | 17/5 | The impact summary will be changed in the customer requirement and will affect the scope, time, cost scope: The scope will be reduced according to the change to 4 modules. Time: The schedule will be increased according to the changes that happen in SRS, Scope statement, Designs, and Development by week. | Nada

## Use Case diagramm
Review No. | Raised By | Issue Date | Issue | Status | Assigend to | Closed date | Closed By
USD_01 | Medhat | 21/4 | Need some more details on the admin use case | Close | Ashry | 22/4 | Medhat
USD_02 | Medhat | 22/4 | No issues found | Close
USD_03 | Saad | 29/4 | Update fuction names | Close | Ashry | 29/4 | Saad
USD_04 | Nada | 13/5 | Remove feedback, rating functions | Close | Ashry | 13/5 | Nada
USD_05 |  |  |  | Close
USD_06 |  |  |  | Close

## Layout Design (wireframe)
Review No. | Raised By | Issue Date | Issue | Status | Assigend to | Closed date | Closed By
WFD_01 | Aya Ahmed | 22/4 | Footer in Home page wrong formated | Close | Medhat | 22/4 | Aya Ahmed
WFD_02 | Ashry | 25/4 | Add Admin page is not found | Open | Nada | 26/4 | Ashry
WFD_03 | Saad | 29/4 | Rereviewed accoding to the new requirments with no issures | Close | Aya | 29/4 | Saad
WFD_04 | Nada | 8/5 | 1. About us in the navigation bar is missed in Layout_Add_Admin Layout_Add_Tour Layout_Add_User 2. The name in the Layout_Add_Admin should be username 3. Tour name is written wrong, Flight_Date is missed, end date is missed, Duration, in the Layout_Add_Tour, Button should be added only. 4. About us button in Tour 1 is redundant as it is already in the navigation bar. 5. Start date should bd end date. 6. Home is missed in the navigation bar in Home in layout_Home. 7. Home for the user is missed as Layout. | Open | Aya | 13/5 | Nada
WFD_05 | Nada | 13/5 | Remove video, rating, and feedback from Layout_Tour, Layout_Add_Tour Instead in Layout_Add_Tour remove video and inset picture. | Close | Aya | 13/5 | Nada
WFD_06 |  |  |  | Close

## QMP
Review No. | Raised By | Issue Date | Issue | Status | Assigend to | Closed date | Closed By
QMP_01 | Aya Ahmed | 15/4 | No issues found | Close
QMP_02 |  |  |  | Close
QMP_03 |  |  |  | Close
QMP_04 |  |  |  | Close
QMP_05 |  |  |  | Close
QMP_06 |  |  |  | Close

## RMP
Review No. | Raised By | Issue Date | Issue | Status | Assigend to | Closed date | Closed By
RMP_01 | Aya Ahmed | 15/4 | No issues found | Close
RMP_02 |  |  |  | Close
RMP_03 |  |  |  | Close
RMP_04 |  |  |  | Close
RMP_05 |  |  |  | Close
RMP_06 |  |  |  | Close

## SRS
Review No. | Raised By | Issue Date | Issue | Status | Assigend to | Closed date | Closed By | Document Status
SRS_V1_R | Aya Ahmed | 12/4 | Version 1.0 |  |  |  |  | Draft
SRS_01 | Nada | 13/4 | No issues found | Close
SRS_02 | Saad | 14/4 | No issues found | Close
SRS_V1.1_R | Aya Ahmed |  | Version 1.1 |  |  |  |  | Draft
SRS_03 | Ashry | 25/4 | The issues are commented in the document | Close | Saad | 26/4 | Ashry
Version 1.2 |  |  | Version 1.2 |  |  |  |  | Draft
SRS_04 | Nada | 29/4 | Home Page REQ-03-Home I think this requirement describes the interface requirement much more, it can describe our system when the user clicks on the view button in every destination available, it will navigate him to the destination page that will have different information about tours, date of the trip, cost, and flight date. | Close | Saad | 29/4 | Nada
SRS_05 | Nada | 29/4 | A.Login REQ-07-Admin_Login I think this is contradictory requirment , with requirment REQ-04-Admin_Login | Close | Saad | 29/4 | Nada
SRS_06 | Nada | 29/4 | Add Admin REQ-01-Add_Admin I think this requiremnt has two different purposes, it can be divided into two requirment sto be clear enough for the developers. | Close | Saad | 29/4 | Nada
SRS_07 | Nada | 29/4 | Add Admin REQ-03-Add_Admin Does the admin will add a name or username ? As this will be contraductory requirment with requirment REQ-02-User_Login. | Close | Saad | 29/4 | Nada
SRS_08 | Nada | 29/4 | Add Tour REQ-01-Add_Tour This requirement missed important information as flight date. | Close | Saad | 29/4 | Nada
Version 1.3 | [7 empty] | Draft
SRS_09 | Amr | 6/5 | REQ_11_SignUp is vague | Close | Saad | 6/5 | Saad
Version 1.4
SRS_10 | Nada | 8/5 | External Interface , wireframe need to be updated. | Open | Aya | 13/5 | Ashry
Version 1.4 | [7 empty] | Draft
SRS_11 | Nada | 13/5 | Updating functional requirments | Close | Ashry | 13/5 | Nada
Version 2.0 | [7 empty] | Draft
SRS_12 | Nada | 17/5 | Update product features and product perspective in administrator. | Close | osama | 17/5
Version 2.1
| Aya Ahmed | 17/6 | the 8 character text are in which language /is user able to enter in arabic language | Close | osama | 19/5
| Aya Ahmed | 17/7 | "It can be a combination of numbers and some special characters _, # " are those only the accepted characters ? | Close | osama | 19/5
| Aya Ahmed | 17/8 | 11 numbers in which format / according to which country // should state that it should start with "01" | Close | osama | 19/5
| Aya Ahmed | 17/9 | is this unique UID is visable to the user ? | Close | osama | 19/5
| Aya Ahmed | 17/10 | what is the content of the confirmation message? | Close | osama | 19/5
| Aya Ahmed | 17/11 | how is it going to search the admin table if no data is entered /should refer to that admin must enter username and password field first? | Close | osama | 19/5
| Aya Ahmed | 17/12 | "a button (add trip) and submit button" what is the diffrence? | Close | osama | 19/5
| Aya Ahmed | 17/13 | what is the curency ? | Close | osama | 19/5
| Aya Ahmed | 17/14 | "Dates should be written by the user and should start from the day it’s recorded" is user able to add tour ? // if is the admin what is meant by recoreded | Close | osama | 19/5
| Aya Ahmed | 17/15 | is admin able to add images from add image button ?? | Close | osama | 19/5
| Aya Ahmed | 17/16 | what is the admin add the same image 2 time ?? | Close | osama | 19/5

## SIQ
Review No. | Raised By | Issue Date | Issue | Status | Assigend to | Closed date | Closed By
SIQ_01 | Ashry | 25/4 | No issues found | Close
SIQ_02 | Amr | 8/5 | Editing Related Features Section | Close | Aya | 8/5 | Aya
Close

## Options (hidden)
Open
Close

## Progress_Chart
PMP | Open | 0 | SRS | Open | 1
| Closed | 0 |  | Closed | 0
| Total | 0 |  | Total | 1

## Scope Statment
Review No. | Raised By | Issue Date | Issue | Status | Assigend to | Closed date | Closed By
SST_01 | Ashry | 2022-04-15 | No issues found | Close
SST_02 | Amr | 8/5 | All dates in constraints assigned in the time section are not correct. | Close | Nada | 8/5 | Nada

## Tracability
Review No. | Raised By | Issue Date | Issue | Status | Assigend to | Closed date | Closed By
TB_01 | Saad | 29/4 | No issues found | Close
TB_02 | Amr | 7/5 | Adding SIQ IDs. | Close | Aya | 08/5 | Aya
TB_03 | Aya | 2022-05-09 | SIQ_11_Tour is repated twice at Customer_Requirement_04 | Close | Aya | 2022-05-09 | Ashry
TB_04 | Aya | 2022-05-09 | Feedback removing is not applied at Customer_Requirement_05 | Close | Aya | 2022-05-09 | Ashry
TB_05 | Aya | 2022-05-09 | SIQ_06_Add_User is not related to Customer_Requirement_09 | Close | Aya | 2022-05-09 | Ashry

## Issue managment
Review No. | Raised By | Issue Date | Issue | Status | Assigend to | Closed date | Closed By
TB_01 | Amr | 2022-05-08 | Update esclation | Close | Ashry | 2022-05-10 | Ashry

## DataBase
Review No. | Raised By | Issue Date | Issue | Status | Assigend to | Closed date | Closed By
DB_01 | Osama | 2022-05-11 | Data types in database is not valid | Close | Ashry | 2022-05-11 | Ashry

## Test Cases
Review No. | Raised By | Issue Date | Issue | Status | Assigend to | Closed date | Closed By
TC_01 | Osama | 2022-05-20 | Home User Page Test cases steps & Precondtions not not described correctly for example in steps you didn't spcified the data for user login | Close | Aya | 2022-05-24 | Aya
TC_02 | Osama | 2022-05-20 | Login Admin Page Test cases steps & Precondtions not not described correctly for example in steps you check the box after clicking login button | Close | Aya | 2022-05-24 | Aya
TC_03 | Osama | 2022-05-25 | TC_User_Sign_Up_007 not correct according REQ-07-Signup in SRS and same in bug report | Close | Nada | 2022-05-25 | Nada
TC_04 | Osama | 2022-05-25 | TC_User_Sign_Up_008 not correct according REQ-07-Signup in SRS and same in bug report | Close | Nada | 2022-05-25 | Nada
TC_05 | Ashry | 2022-05-25 | Actual result in missing in BookUser TC | Open | Nada | 2022-05-25
TC_06 | Ashry | 2022-05-25 | Testcase number "TC_User_Book_004" the discription should be about home not "About us" button | Open | Nada | 2022-05-25