## Sheet1
Comment ID | Concerining which file | Comment By | Comment date | Comment | state | Assigned to | close date
comment_01 | PMP | Amr Mokhtar | 2022-05-04 | No document revision table in the PMP | closed | Nada | 2022-07-05
comment_02 | SMP | Amr Mokhtar | 2022-05-04 | the timeline of the project only mentions 5 weeks no specific date | closed | Nada | 2022-07-05
comment_03 | CM | Amr Mokhtar | 2022-05-04 | the CM plan isn't defined | closed | Osama | 2022-09-05
comment_04 | PMP/Issue management | Amr Mokhtar | 2022-05-04 | please add more details into escalation seciton | closed | Ashry | 2022-10-05
comment_05 | PMP | Amr Mokhtar | 2022-05-04 | PMP only reviewed once by the team and the comments from customer not added | closed | Nada | 2022-10-05
comment_06 | PMP | Amr Mokhtar | 2022-05-04 | multiple uploads while only 2 reviews are done | closed | Nada | 2022-10-05
comment_07 | reviews | Amr Mokhtar | 2022-05-04 | no review strategy is unified the requirements are reviewed not by checklist. | closed | Medhat | 2022-10-05
comment_08 | Tracibility matrix | Amr Mokhtar | 2022-05-04 | how you will handle more than one review of PMP Tracibility | closed | Nada | 2022-10-05
comment_09 | Tracibility matrix | Amr Mokhtar | 2022-05-04 | only SRS has IDS it should be all levels | closed | Aya | 2022-07-05
comment_10 | SRS | Amr Mokhtar | 2022-05-04 | REQ-11Signup is vague | closed | saad | 2022-06-05
comment_11 | SRS | Amr Mokhtar | 2022-05-04 | only one version is added in the version control on 14/4 but the document was updated after that date. | closed | ashry | 2022-07-05
comment_12 | Design | Amr Mokhtar | 2022-05-04 | no interfaces between modules | closed | Nada | 13/5/2022
comment_13 | Design | Amr Mokhtar | 2022-05-04 | no modules of the system | closed | Nada | 13/5/2022
comment_14 | Design | Amr Mokhtar | 2022-05-04 | LLD is missing | closed | Aya | 2022-10-05
comment_01 | Design | Auditer\ Mohamed Hassan | 15/5/20222 | The message in the login sequence diagram need to be the same message as the same as the message written in the SRS and in the code in the system. | closed | Nada | 17/5/2022
comment_02 | Design | Amr Mokhtar | 15/5/2022 | The sequence diagram should be added to the high-level design and removed from LLD. | closed | Nada | 17/5/2022
comment_03 | Impact analysis | Amr Mokhtar | 15/5/2022 | Impact analysis should be re-written again. | closed | Nada | 17/5/2022
comment_01 | Test Cases | Amr Mokhtar | 22/5/20222 | The test cases data steps is unclear enough. | closed | Aya | 24/5/2022
comment_02 | Test Cases | Auditer\Mohamed Hassan | 22/5/20222 | The test case in user book is unclear in precondition. | closed | Nada | 25/5/2022
comment_03 | Test Cases | Auditer\Mohamed Hassan | 22/5/20222 | The test case in user book is missing REQ-03-Tour. | closed | Nada | 25/5/2022
comment_04 | RTM | Auditer\Mohamed Hassan | 15/5/2022 | RTM must be reviewed against SRS. | open | All Team