## Add Tour Admin Page
ID | Title | Description | precondtion | steps | expected result | actual result | status | Priority | Severity | Author | Date
AddTour_001 | Add Tour Flight and End Date | The flight date must be before the end date field but when setting the flight data before the end date no error message is appear. | "-Visual Studio with .net framework above 4.5 -Chrome Browser is an available version. -Website is accessed successfully." | 1-Run the project from Visual Studio. 2-Enter username field with "admin" 3-Enter password filed with "admin" 4-Check the checkbox is admin 5-Click Login 6-Click Add Tour button 7-Enter in the flight date"10/06/2022" 8-Enter in the end date"30/05/2022" 9-Click submit. | An error message must appear that “You can’t set the end date before the start date or vice versa”, | No Errors appear in flight or end date fields | Opened | Medium | Minor | Osama | 24/05/2022

## Login User Page
ID | Title | Description | precondtion | steps | expected result | actual result | status | Priority | Severity | Author | Date
LoginUser_001 | Login Page | Check website behaviour when click on About us text | 1- Updated version of code 2- visual studio 3- Updated SRS document 4- accessed web browser | 1- open visual studio and run the web browser 2- You will be navigated to login page automaticlly 3-click on About us text that appears on the top right corner | the browser should be navigated to the bottom of the login page, then you will see about us section | Nothing appears | Opened | Medium | Minor | Ashry | 25/5/2022

## Sign Up User Page
ID | Title | Description | precondtion | steps | expected result | actual result | status | Priority | Severity | Author | Date
User_Sign_Up_001 | Sign up using valid fields. | Validate that email doesn't accept special character except "_ , #". | 1- Updated version of code 2- visual studio 3- Updated SRS document 4- accessed web browser 5- accessed database | 1- open visual studio and run the web browser 2- After applying steps in preconditions you will be navigated to a sign-up page. 3- Username = "user" Email = "user_1999!*@gmail.com" Password= "Uo123456" Confirm Password= "Uo123456" Mobile Number = 01114557891 Age= 23 4- click sign-up button. 5- check if user added to database | msg displayed "email doesn't apply to the required format". | Data is stored in the database and the user redirects to the login page. | open | meduim | Minor | nada | 25/05/2022
User_Sign_Up_002 | Sign up using valid fields. | Validate that the password field doesn't accept special characters. | 1- Updated version of code 2- visual studio 3- Updated SRS document 4- accessed web browser 5- accessed database | 1- open visual studio and run the web browser 2- After applying steps in preconditions you will be navigated to a sign-up page. 3- Username = "user" Email = "user_1999@gmail.com" Password= "Uo12345@" Confirm Password= "Uo12345@" Mobile Number = 01114557891 Age= 23 4- click sign-up button. 5- check if user added to database | msg displayed "password doesn't apply to the required format". | Data is stored in the database and the user redirects to the login page. | open | meduim | Minor | nada | 25/05/2022
User_Sign_Up_003 | Sign up using valid fields. | Validate that the password field doesn't accept more than 8 characters. | 1- Updated version of code 2- visual studio 3- Updated SRS document 4- accessed web browser 5- accessed database | 1- open visual studio and run the web browser 2- After applying steps in preconditions you will be navigated to a sign-up page. 3- Username = "user" Email = "user_1999@gmail.com" Password= "Uo12345678" Confirm Password= "Uo12345678" Mobile Number = 01114557891 Age= 23 4- click sign-up button. 5- check if user added to database | msg displayed "password doesn't apply to the required format". | Data is stored in the database and the user redirects to the login page. | open | meduim | Minor | nada | 25/05/2022
User_Sign_Up_004 | Sign up using valid fields. | Validate that the confirm password should match the passowrd field. | 1- Updated version of code 2- visual studio 3- Updated SRS document 4- accessed web browser 5- accessed database | 1- open visual studio and run the web browser 2- After applying steps in preconditions you will be navigated to a sign-up page. 3- Username = "user" Email = "user_1999@gmail.com" Password= "Uo123456" Confirm Password= "Uo12345K" Mobile Number = 01114557891 Age= 23 4- click sign-up button. 5- check if user added to database | msg displayed "confirm password doesn't match to the password". | no messages appear | open | meduim | Minor | nada | 25/05/2022

## Login Admin Page
ID | Title | Description | precondtion | steps | expected result | actual result | status | Priority | Severity | Author | Date
Admin_Login_001 | loging with invalid username format as number | when loging to the system with invaild username format and valid password format with checking isadmin checkbox no error msg is displayed to the user | 1- Updated version of code 2- visual studio is opened and correct version of code is running 3- Updated SRS document 4- accessed web browser opened at login page | 1-write "7777" as username 2-write "admin" as password 3-click on login | a "please insert data based on the required format" message should be displayed | a "Please create an account first and then login" is displayed | open | low | Minor | aya | 24/05/2022
Admin_Login_002 | loging with invalid password format as charcters only | when loging to the system with valid username format and invalid password format with checking isadmin checkbox user is directed to create an account msg not error format msg | 1- Updated version of code 2- visual studio is opened and correct version of code is running 3- Updated SRS document 4- accessed web browser opened at login page | 1-write "admin" as username 2-write "*****" as password 3-click on login 4-observe the msg | a "please insert data based on the required format" message should be displayed | a "Please create an account first and then login" is displayed | open | meduim | Minor | aya | 24/05/2022
Admin_Login_003 | loging with invalid username and valid password format | when loging to the system with invaild username as arabic charactes and valid password format with checking isadmin checkbox user is directed to create account msg and no error format msg is displayed | 1- Updated version of code 2- visual studio is opened and correct version of code is running 3- Updated SRS document 4- accessed web browser opened at login page | 1-write "admin" as username 2-write "ايه" as password 3-click on login 4-check isadmin checkbox 5-observe the msg | a "please insert data based on the required format" message should be displayed | a "Please create an account first and then login" should be displayed | open | meduim | Minor | aya | 24/05/2022