## Sheet1
RCIA TABLE
| PROJECT TITLE | PROJECT ID | COMPANY |  | Letter | abbreviation | DATE | VERSION
| Travel Advisor Web Application | Team D | ITI |  | R | Resposible | 2022-12-04 | 1.0.0
[5 empty] | C | Consultant
[5 empty] | I | Informed
[5 empty] | A | Accountable
TASK ID | TASK DESCRIPTION | Muhammad Ashry | Ahmed Medhat | Aya Ahmed | Nada Abdelrehem | Saad Hamdy
1 | Initiation
1.1 | Identify Stakeholder |  |  |  | C | R
1.1.1 | SRS | C | C | R | A | I
1.1.2 | Project Charter | I | I | I | C | R
2 | Planning
2.1 | Project Management Plan | I | A | A | C | R
2.1.1 | Scope Management Plan | A | I |  | C | R
2.1.2 | Change Management Plan | A | I | I | C | R
2.1.3 | Schedule Time Management | I | A | I | C | R
2.1.3.1 | MileStones
2.1.3.2 | Project Schedule | I | A | I | R | C
2.1.3.3 | Dependencies | I | A | I | C | R
2.1.4 | Quality Managemnt Plan | I | I | A | C | R
2.1.5 | Configuration Management Plan | A | I | I | C | R
2.1.6 | Commuincation Management Plan | I | I | A | C | R
2.1.6.1 | Commuincation Matrix | A | A | A | C | R
2.1.7 | Risk Management Plan | I | A | I | C | R
2.1.7.1 | Risk Log | A/I | A/I | A/I | C | R
3 | Implementation and Execurion
3.1 | Solution Design
3.1.1 | Prototype | I | I | R | A | C
3.1.2 | Layout Design | I | R | I | C/A | C
3.2 | Design
3.2.1 | Front-End Design | A | R | A | C | I
3.2.2 | Back-End Design | A | A | C | R | C
3.3 | Development
3.3.1 | Front-End Development | C | R | A | C | I
3.3..2 | Back-End Development | C | C | R | A | I
3.4 | Content & SEO
3.5 | Testing
3.5.1 | Experience-Based Testing | R | A | A | C | C
4 | Mointoring and Control
4.1 | Traceability Matrix | A | I | I | I | R
4.2 | Version Control | A | I | I | I | R
5 | Closing
5.1 | Deployment Phase | A | A | C | A | R