## WBS Dictionary
WORK BREAKDOWN STRUCTURE DICTIONARY
| PROJECT TITLE | PROJECT ID | COMPANY |  |  | DATE | VERSION
| Travel Advisor Web Application | Team D | ITI |  |  | 2022-12-04 | 1.0.0
TASK ID | TASK DESCRIPTION | DEPENDENT UPON | TASK OWNER | TASK STATUS | BEGIN DATE | ESTIMATED DATE OF COMPLETION | ACTUAL DATE OF COMPLETION | ADDITIONAL INFO
1 | Initiation | (TASK ID) |  | 0%
1.1 | Identify Stakeholder |  |  | 0%
1.1.1 | SRS |  |  | 0%
1.1.2 | Project Charter |  |  | 0%
2 | Planning |  |  | 0%
2.1 | Project Management Plan |  |  | 0%
2.1.1 | Scope Management Plan |  |  | 0%
2.1.2 | Change Management Plan |  |  | 0%
2.1.3 | Schedule Time Management |  |  | 0%
2.1.3.1 | MileStones |  |  | 0%
2.1.3.2 | Project Schedule |  |  | 0%
2.1.3.3 | Dependencies |  |  | 0%
2.1.4 | Quality Managemnt Plan
2.1.5 | Configuration Management Plan |  |  | 0%
2.1.6 | Commuincation Management Plan |  |  | 0%
2.1.6.1 | Commuincation Matrix |  |  | 0%
2.1.7 | Risk Management Plan |  |  | 0%
2.1.7.1 | Risk Log |  |  | 0%
3 | Implementation and Execurion |  |  | 0%
3.1 | Solution Design |  |  | 0%
3.1.1 | Prototype |  |  | 0%
3.1.2 | Layout Design |  |  | 0%
3.2 | Design |  |  | 0%
3.2.1 | Front-End Design |  |  | 0%
3.2.2 | Back-End Design |  |  | 0%
3.3 | Development |  |  | 0%
3.3.1 | Front-End Development |  |  | 0%
3.3..2 | Back-End Development |  |  | 0%
3.4 | Content & SEO |  |  | 0%
3.5 | Testing |  |  | 0%
3.5.1 | Experience-Based Testing |  |  | 0%
4 | Mointoring and Control |  |  | 0%
4.1 | Traceability Matrix |  |  | 0%
4.2 | Version Control |  |  | 0%
5 | Closing |  |  | 0%
5.1 | Deployment Phase |  |  | 0%