## Sheet1
Date | Who asked | ID | Related Feature | Questions | Answer | Date | Who Answered | Status
2022-04-09 | Saad | SIQ_01 | Booking module | What is the steps of Booking a Flight? | We will simulate the booking processes with a simple book button with no database constraints |  | Eng. Amr | FALSE
2022-04-09 | Aya | SIQ_02 | Registration user module | what are the types of users? | 2 kind of users only (admin,customer) no guest user |  | Eng. Amr | FALSE
2022-04-09 | Saad | SIQ_03 | Tours Module | What are the data needed for the tours? | budget, destination |  | Eng. Amr | FALSE
2022-04-09 | Aya | SIQ_04 | Registration user | What are the data needed for user registeration form? | first name , last name, password, email, age only |  | Eng. Amr | FALSE
2022-04-09 | Saad | SIQ_05 | Registration admin module | How should the admin register & login? | constant credentials for admin to log |  | Eng. Amr | FALSE
2022-04-09 | Aya | SIQ_06 | Admin Authorization module | What are the admin features ? | 1- Adding new tour 2- Add user 3- Add admin |  | Eng. Amr | FALSE
2022-04-09 | Saad | SIQ_07 | Booking module | Who can rate a trip? | user who already traveled using our system and should recieve mail after completing the trip to rate ( 5 start ratting ) |  | Eng. Amr | FALSE
2022-04-09 | Ashry | SIQ_08 | Booking module | Will the booking be on external or internal platform ? | It will be a simple button to simulate the booking |  | Eng. Amr | FALSE
2022-04-09 | Ashry | SIQ_09 | UI design module | is there any UI design requirments ? | no conistaints on the design ,a prototype is needed |  | Eng. Amr | FALSE
2022-04-09 | Medhat | SIQ_10 | NA | How user is going to pay for the trip ? | no payment functions in te system |  | Eng. Amr | FALSE
2022-04-09 | Medhat | SIQ_11 | Booking module | How user will know the booking is confirmed ? | a conifrmation mail will be sent ,and message stating that booking was successfully done |  | Eng. Amr | FALSE
2022-04-09 | Medhat | SIQ_12 | Rating Module | how trips are displayed to the user? | top rated first will be displayed |  | Eng. Amr | FALSE
2022-04-09 | Nada | SIQ_13 | Rating Module | what user can send his feedback ? | user can write his feedback in a text field |  | Eng. Amr | FALSE
2022-04-09 | Ashry | SIQ_14 | Product Type | what is meant by PC Based ? | web based (Browesr){ie, firefox, chrome} |  | Eng. Amr | FALSE
2022-04-09 | Nada | SIQ_15 | Registration user module | is there is any requirments regarding user unquie id ? | auto generated |  | Eng. Amr | FALSE
2022-04-09 | Nada | SIQ_16 | UI design module | what is the system workflow? | user must log in first, then a list of top rated trips will be displayed to choose and book |  | Eng. Amr | FALSE
2022-04-11 | Nada | SIQ_17 | Login Module | what kind of actions needed to handle user login problems three times a row ? | No actions needed |  | Eng. Amr | FALSE
2022-04-11 | Nada | SIQ_18 | NA | do the system has sponsors and is there is any external resourses or budget? | No external resources and budgets |  | Eng. Amr | FALSE
2022-04-11 | Nada | SIQ_19 | NA | Dose the system provide partnership with travel agencies ? | We are a new travel agent with a website. |  | Eng. Amr | FALSE
Assumptions
Ashry |  |  | we are developing using c#
Ashry |  |  | Browsers: Chrome, Firefox and Edge.
Ashry |  |  | Operating System: 8, 10, 11
Ashry |  |  | Recommended Conf.: 256mb RAM or higher, 10mb Disk space
Ashry |  |  | Screen Resolution: 1024x768
Aya |  |  | Requests done by the user (login,view trips,booking,ratting and feedback ) should be performed in less than 20 seconds
Hardware & Software Assumptions
Processor |  |  | Pentium IV
Speed |  |  | 2.0 GHZ above
Hard Disk |  |  | 40 GB
RAM |  |  | 512 MB
CD Drive |  |  | 48x
Input devices |  |  | Keyboard and mouse
Monitor |  |  | Compatible monitor with 600 x 800 resolutions
Internet |  |  | 100kbps above
Operating System |  |  | Windows 7 or Higher versions
Front End |  |  | .NET
Back End |  |  | SQL