## Sheet1
Comment ID | Concerining which file | Comment By | Comment date | Comment | state | Assigned to | close date
comment_01 | PMP | Amr Mokhtar | 2022-05-04 | No document revision table in the PMP | closed | Nada | 2022-07-05
comment_02 | SMP | Amr Mokhtar | 2022-05-04 | the timeline of the project only mentions 5 weeks no specific date | closed | Nada | 2022-07-05
comment_03 | CM | Amr Mokhtar | 2022-05-04 | the CM plan isn't defined | open
comment_04 | PMP/Issue management | Amr Mokhtar | 2022-05-04 | please add more details into escalation seciton | open
comment_05 | PMP | Amr Mokhtar | 2022-05-04 | PMP only reviewed once by the team and the comments from customer not added | open
comment_06 | PMP | Amr Mokhtar | 2022-05-04 | multiple uploads while only 2 reviews are done | closed
comment_07 | reviews | Amr Mokhtar | 2022-05-04 | no review strategy is unified the requirements are reviewed not by checklist. | open
comment_08 | Tracibility matrix | Amr Mokhtar | 2022-05-04 | how you will handle more than one review of PMP Tracibility | open
comment_09 | Tracibility matrix | Amr Mokhtar | 2022-05-04 | only SRS has IDS it should be all levels | closed | Aya | 2022-07-05
comment_10 | SRS | Amr Mokhtar | 2022-05-04 | REQ-11Signup is vague | closed | saad | 2022-06-05
comment_11 | SRS | Amr Mokhtar | 2022-05-04 | only one version is added in the version control on 14/4 but the document was updated after that date. | closed | ashry | 2022-07-05
comment_12 | Design | Amr Mokhtar | 2022-05-04 | no interfaces between modules | open
comment_13 | Design | Amr Mokhtar | 2022-05-04 | no modules of the system | open
comment_14 | Design | Amr Mokhtar | 2022-05-04 | LLD is missing | open