## PMP
Review No. | Raised By | Issue Date | Issue | Status | Assigend to | Closed date | Closed By | Document Status
Version 1.0 | [7 empty] | Draft
PMP_01 | Aya Ahmed | 14/4 | No issue found | Close
PMP_02 | Ashry | 15/4 | No issue found | Close
PMP_03 | Medhat | 15/4 | No issue found | Close
Version 1.1 |  |  | Version 1.0 |  |  |  |  | Draft
PMP_04 | Ashry | 25/4 | More required edits in escaltion | Close | Saad | 25/4 | Ashry
Version 1.2 | [7 empty] | Draft
PMP_05 | Medhat | 29/4 | Naming Convention is required | Close | Saad | 29/4 | Medhat
Version 1.3 | [7 empty] | Draft
PMP_06 | Amr | 8/5 | Revision History is missed | Close | Nada | 8/5 | Nada

## Project Charter
Review No. | Raised By | Issue Date | Issue | Status | Assigend to | Closed date | Closed By
PC_01 | Amr | 8/5 | In organizational goals , delivery date is missed. | Closed | Nada | 8/5 | Nada

## Sequence Diagrams
Review No. | Raised By | Issue Date | Issue | Status | Assigend to | Closed date | Closed By
SEQ_01 | Saad | 22/4 | Admin Add trip has some duplicated data | Close | Aya | 22/4 | Saad
SEQ_02 | Saad | 22/4 | No issues found | Close
SEQ_03 | Ashry | 22/4 | No issues found | Close
SEQ_04 | Amr | 6/5 | Home , Thank you page in Sequence_User_Book is redudant. | Close | Nada | 8/5 | Nada
SEQ_05 |  |  |  | Close
SEQ_06 |  |  |  | Close

## ERD diagram
Review No. | Raised By | Issue Date | Issue | Assigend to | Closed date | Closed By
ERD_01 | Nada | 21/4 | The relation "Book" between customer and destination is not recorded | Saad | 22/4 | Nada
ERD_02 | Nada | 22/4 | No issue found
ERD_03 | Medhat | 22/4 | No issue found
ERD_04 | Ashry | 29/4 | No issue found
ERD_05 | Nada | 8/5 | In admin entity, name of the admin should be username, In User entity, username is missed. In Tour entity, start date should be end date. | Aya
ERD_06

## Use Case diagramm
Review No. | Raised By | Issue Date | Issue | Status | Assigend to | Closed date | Closed By
USD_01 | Medhat | 21/4 | Need some more details on the admin use case | Close | Ashry | 22/4 | Medhat
USD_02 | Medhat | 22/4 | No issues found | Close
USD_03 | Saad | 29/4 | Update fuction names | Close | Ashry | 29/4 | Saad
USD_04 |  |  |  | Close
USD_05 |  |  |  | Close
USD_06 |  |  |  | Close

## Layout Design (wireframe)
Review No. | Raised By | Issue Date | Issue | Status | Assigend to | Closed date | Closed By
WFD_01 | Aya Ahmed | 22/4 | Footer in Home page wrong formated | Close | Medhat | 22/4 | Aya Ahmed
WFD_02 | Ashry | 25/4 | Add Admin page is not found | Open | Nada | 26/4 | Ashry
WFD_03 | Saad | 29/4 | Rereviewed accoding to the new requirments with no issures | Close | Aya | 29/4 | Saad
WFD_04 | Nada | 8/5 | 1. About us in the navigation bar is missed in Layout_Add_Admin Layout_Add_Tour Layout_Add_User 2. The name in the Layout_Add_Admin should be username 3. Tour name is written wrong, Flight_Date is missed, end date is missed, Duration, in the Layout_Add_Tour, Button should be added only. 4. About us button in Tour 1 is redundant as it is already in the navigation bar. 5. Start date should bd end date. 6. The rating is missed in Tour1 where user can insert his rating. 7. Home is missed in the navigation bar in Home in layout_Home. 8. Home for the user is missed as Layout. | Open | Aya
WFD_05 |  |  |  | Close
WFD_06 |  |  |  | Close

## QMP
Review No. | Raised By | Issue Date | Issue | Status | Assigend to | Closed date | Closed By
QMP_01 | Aya Ahmed | 15/4 | No issues found | Close
QMP_02 |  |  |  | Close
QMP_03 |  |  |  | Close
QMP_04 |  |  |  | Close
QMP_05 |  |  |  | Close
QMP_06 |  |  |  | Close

## RMP
Review No. | Raised By | Issue Date | Issue | Status | Assigend to | Closed date | Closed By
RMP_01 | Aya Ahmed | 15/4 | No issues found | Close
RMP_02 |  |  |  | Close
RMP_03 |  |  |  | Close
RMP_04 |  |  |  | Close
RMP_05 |  |  |  | Close
RMP_06 |  |  |  | Close

## SRS
Review No. | Raised By | Issue Date | Issue | Status | Assigend to | Closed date | Closed By | Document Status
SRS_V1_R | Aya Ahmed | 12/4 | Version 1.0 |  |  |  |  | Draft
SRS_01 | Nada | 13/4 | No issues found | Close
SRS_02 | Saad | 14/4 | No issues found | Close
SRS_V1.1_R | Aya Ahmed |  | Version 1.1 |  |  |  |  | Draft
SRS_03 | Ashry | 25/4 | The issues are commented in the document | Close | Saad | 26/4 | Ashry
Version 1.2 |  |  | Version 1.2 |  |  |  |  | Draft
SRS_04 | Nada | 29/4 | Home Page REQ-03-Home I think this requirement describes the interface requirement much more, it can describe our system when the user clicks on the view button in every destination available, it will navigate him to the destination page that will have different information about tours, date of the trip, cost, and flight date. | Close | Saad | 29/4 | Nada
SRS_05 | Nada | 29/4 | A.Login REQ-07-Admin_Login I think this is contradictory requirment , with requirment REQ-04-Admin_Login | Close | Saad | 29/4 | Nada
SRS_06 | Nada | 29/4 | Add Admin REQ-01-Add_Admin I think this requiremnt has two different purposes, it can be divided into two requirment sto be clear enough for the developers. | Close | Saad | 29/4 | Nada
SRS_07 | Nada | 29/4 | Add Admin REQ-03-Add_Admin Does the admin will add a name or username ? As this will be contraductory requirment with requirment REQ-02-User_Login. | Close | Saad | 29/4 | Nada
SRS_08 | Nada | 29/4 | Add Tour REQ-01-Add_Tour This requirement missed important information as flight date. | Close | Saad | 29/4 | Nada
Version 1.3 | [7 empty] | Draft
SRS_09 | Amr | 6/5 | REQ_11_SignUp is vague | Close | Saad | 6/5 | Saad
Version 1.4
SRS_10 | Nada | 8/5 | External Interface , wireframe need to be updated. | Open | Aya

## SIQ
Review No. | Raised By | Issue Date | Issue | Status | Assigend to | Closed date | Closed By
SIQ_01 | Ashry | 25/4 | No issues found | Close
SIQ_02 | Amr | 8/5 | Editing Related Features Section | Close | Aya | 8/5 | Aya
Close

## Options (hidden)
Open
Close

## Progress_Chart
PMP | Open | 0 | SRS | Open | 1
| Closed | 0 |  | Closed | 0
| Total | 0 |  | Total | 1

## Scope Statment
Review No. | Raised By | Issue Date | Issue | Status | Assigend to | Closed date | Closed By
SST_01 | Ashry | 2022-04-15 | No issues found | Close
SST_02 | Amr | 8/5 | All dates in constraints assigned in the time section are not correct. | Close | Nada | 8/5 | Nada
Close

## Tracability
Review No. | Raised By | Issue Date | Issue | Status | Assigend to | Closed date | Closed By
TB_01 | Saad | 29/4 | No issues found | Close
TB_02 | Amr | 7/5 | Adding SIQ IDs. | Close | Aya | 8/5 | Aya
Close